## Read Me
1 | This calendar is for Essential SAFe only
2 | This workbook depicts the a typical calaendar of an ART which consists of:
Three Agile Teams - Team A, Team B, Team C
Each team has one Scrum Master (SM), one Product Owner (PO), an five to seven Development Team (DevTeam) memebers
3 | The iteration duration of this ART is two weeks.
Iterations' firt day is Tuesday.
ART consists of three Development Iterations ( 2 weeks each) and one week of Innovation & Planning Iteration.
4 | The SoS and PO Sync is on alternate days. Depending upon context occurance of these meetings may vary from daily to weekly.
5 | The ART Sync meeting is once in a week. It may be once in an iterartion as well.
6 | While setting up the calendar ensure that
7 |  | PI meeting span to consequitive days (no breaks).
Avoid Friday's to schedule any thing significant as people might be in weekend mood and long weekends may affect.
Time difference among different locations (if teams are distributed) is taken care of.
8 | Some of the meetings & interactions are spanned across the Iteraration to depict that specific meetings need to be scheduled as per context.
9 | The meetings depicting here are not the only one. For example RTE need to work withing Lean Budget which requires interaction with budgeting authority as well.
10 | Scrum Master may ask one or more devTeam member to join him in SoS meeting if needed.
11 | Product Owner may ask one or more devTeam member to join him in PO Sync meeting if needed.
This is wook in Progress, please share feedback to improve it.

## AgileTeam
2018-02-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on | Tue | Wed
[6 empty] | 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Team A SM | [11 empty] | DS A,1,1 SP A,1,1 | DS A, 1, 2 | DS A, 1, 3 | DS A, 1, 4 |  |  | DS A, 1, 5 | DS A, 1, 6 | DS A, 1, 7 | DS A, 1, 8 | DS A, 1, 9 |  |  | DS A, 1, 10 SR A, 1, 1 Retro A, 1, 1 | System Demo ABC, 1, 1 | DS A,2,1 SP A, 2,1 | DS A, 2, 2 | DS A, 2, 3 | DS A, 2, 4 |  |  | DS A, 2, 5 | DS A, 2, 6 | DS A, 2, 7
Team B SM | [11 empty] | DS B,1,1 SP B,1,1 | DS B, 1, 2 | DS B, 1, 3 | DS B, 1, 4 |  |  | DS B, 1, 5 | DS B, 1, 6 | DS B, 1, 7 | DS B, 1, 8 | DS B, 1, 9 |  |  | DS B, 1, 10 SR B, 1, 1 Retro B, 1, 1 |  | DS B, 2,1 SP B, 2,1 | DS B, 2, 2 | DS B, 2, 3 | DS B, 2, 4 |  |  | DS B, 2, 5 | DS B, 2, 6 | DS B, 2, 7
Team C SM | [11 empty] | DS C,1,1 SP C,1,1 | DS C, 1, 2 | DS C, 1, 3 | DS C, 1, 4 |  |  | DS C, 1, 5 | DS C, 1, 6 | DS C, 1, 7 | DS C, 1, 8 | DS C, 1, 9 |  |  | DS C, 1, 10 SR C, 1, 1 Retro , 1, 1 |  | DS C,2,1 SP C,2,1 | DS C, 2, 2 | DS C, 2, 3 | DS C, 2, 4 |  |  | DS C, 2, 5 | DS C, 2, 6 | DS C, 2, 7
2018-03-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on | Tue | Wed | Thru | Fri | Sat
[6 empty] | 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Team A SM | [5 empty] | DS A, 2, 8 | DS A, 2, 9 |  |  | DS A, 2, 10 SR A, 2, 1 Retro A, 1, 1 | System Demo ABC, 2, 1 | DS A,3,1 SP A,3,1 | DS A, 3, 2 | DS A, 3, 3 | DS A, 3, 4 |  |  | DS A, 3, 5 | DS A, 3, 6 | DS A, 3, 7 | DS A, 3, 8 | DS A, 3, 9 |  |  | DS A, 3, 10 SR A, 3, 1 Retro A, 3, 1 | System Demo ABC, 3, 1 | DS A,4,1 SP A, 4,1 | DS A, 4, 2 | DS A, 2, 3 | DS A, 4, 4 |  |  | DS A, 4, 5 | DS A, 4, 6 | DS A, 4, 7 | DS A, 4, 8 | DS A, 4, 9
Team B SM | [5 empty] | DS B, 2, 8 | DS B, 2, 9 |  |  | DS B, 2, 10 SR B, 2, 1 Retro B, 1, 1 |  | DS B,3,1 SP B,3,1 | DS B, 3, 2 | DS B, 3, 3 | DS B, 3, 4 |  |  | DS B, 3, 5 | DS B, 3, 6 | DS B, 3, 7 | DS B, 3, 8 | DS B, 3, 9 |  |  | DS B, 3, 10 SR B,31, 1 Retro B, 3, 1 |  | DS B, 4,1 SP B, 4,1 | DS B, 4, 2 | DS B, 4, 3 | DS B, 4, 4 |  |  | DS B, 4, 5 | DS B, 4, 6 | DS B, 4, 7 | DS B, 4, 8 | DS B, 4, 9
Team C SM | [5 empty] | DS C, 2, 8 | DS C, 2, 9 |  |  | DS C, 2, 10 SR C, 2, 1 Retro , 2, 1 |  | DS C,3,1 SP C,3,1 | DS C, 3, 2 | DS C, 3, 3 | DS C, 3, 4 |  |  | DS C, 3, 5 | DS C, 3, 6 | DS C, 3, 7 | DS C, 3, 8 | DS C, 3, 9 |  |  | DS C, 3, 10 SR C, 3, 1 Retro , 3, 1 |  | DS C,4,1 SP C,4,1 | DS C, 4, 2 | DS C, 4, 3 | DS C, 4, 4 |  |  | DS C, 4, 5 | DS C, 4, 6 | DS C, 4, 7 | DS C, 4, 8 | DS C, 4, 9
2018-04-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on
| 1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  | 24 | 25 | 26 | 27 | 28 | 29 | 30
Team A SM |  | DS A, 4, 10 | System Demo ABC, 4, 1 | [8 empty] | DS A,1,1 SP A,1,1 | DS A, 1, 2 | DS A, 1, 3 | DS A, 1, 4 |  |  | DS A, 1, 5 | DS A, 1, 6 | DS A, 1, 7 | DS A, 1, 8 | DS A, 1, 9 |  |  | DS A, 1, 10 SR A, 1, 1 Retro A, 1, 1 | System Demo ABC, 1, 1 | DS A,2,1 SP A, 2,1 | DS A, 2, 2 | DS A, 2, 3 | DS A, 2, 4 |  |  | DS A, 2, 5
Team B SM |  | DS B, 4, 10 | [9 empty] | DS B,1,1 SP B,1,1 | DS B, 1, 2 | DS B, 1, 3 | DS B, 1, 4 |  |  | DS B, 1, 5 | DS B, 1, 6 | DS B, 1, 7 | DS B, 1, 8 | DS B, 1, 9 |  |  | DS B, 1, 10 SR B, 1, 1 Retro B, 1, 1 |  | DS B, 2,1 SP B, 2,1 | DS B, 2, 2 | DS B, 2, 3 | DS B, 2, 4 |  |  | DS B, 2, 5
Team C SM |  | DS C, 4, 10 | [9 empty] | DS C,1,1 SP C,1,1 | DS C, 1, 2 | DS C, 1, 3 | DS C, 1, 4 |  |  | DS C, 1, 5 | DS C, 1, 6 | DS C, 1, 7 | DS C, 1, 8 | DS C, 1, 9 |  |  | DS C, 1, 10 SR C, 1, 1 Retro , 1, 1 |  | DS C,2,1 SP C,2,1 | DS C, 2, 2 | DS C, 2, 3 | DS C, 2, 4 |  |  | DS C, 2, 5
Legends
DS: Daily Standup
SP: Iteration Planning
SR: Iteration Review
Team, Iteration, #
Exploring & researching next PI
Pre PI Planning Context Setting and Readiness
I & A Workshop
PI Planning
Post PI Planning
PI Planning (Distributed Teams)
Continuing Education & Training
Post PI Planning
PI Planning (Distributed Teams)
PI Planning

## Scrum Master
2018-02-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on | Tue | Wed
[6 empty] | 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Team A SM | [11 empty] | DS A,1,1 SP A,1,1 SoS ABC,1,1 | DS A,1,2 | DS A,1,3 SoS ABC,1,2 | DS A,1,4 |  |  | DS A,1,5 SoS ABC,1,3 | DS A,1 6 | DS A,1,7 SoS ABC,1,4 | DS A,1,8 | DS A,1,9 SoS ABC,1,5 |  |  | DS A,1,10 SR A,1,1 Retro A,1,1 | System Demo ABC, 1, 1 | DS A,2,1 SP A,2,1 SoS ABC,2,1 | DS A,2,2 | DS A,2,3 SoS ABC,2,2 | DS A,2,4 |  |  | DS A,2,5 SoS ABC,2,3 | DS A,2,6 | DS A,2,7 SoS ABC,2,4
2018-03-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on | Tue | Wed | Thru | Fri | Sat
[6 empty] | 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Team A SM | [5 empty] | DS A,2,8 | DS A,2,9 SoS ABC,2,5 |  |  | DS A,2,10 SR A,2,1 Retro A,1,1 | System Demo ABC, 2, 1 | DS A,3,1 SP A,3,1 SoS ABC,3,1 | DS A,3,2 | DS A, 3, 3 SoS ABC,3,2 | DS A,3,4 |  |  | DS A,3,5 SoS ABC,3,3 | DS A,3,6 | DS A,3,7 SoS ABC,3,4 | DS A,3,8 | DS A,3,9 SoS ABC,3,5 |  |  | DS A,3,10 SR A,3,1 Retro A,3,1 | System Demo ABC, 3, 1 | DS A,4,1 SP A,4,1 SoS ABC,4,1 | DS A,4,2 | DS A,2,3 SoS ABC,4,2 | DS A,4,4 |  |  | DS A, 4, 5 SoS ABC,4,3 | DS A,4,6 | DS A, 4, 7 SoS ABC,4,4 | DS A,4,8 | DS A,4,9 SoS ABC,4,5
2018-04-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on
| 1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  | 24 | 25 | 26 | 27 | 28 | 29 | 30
Team A SM |  | DS A, 4, 10 | System Demo ABC, 4, 1 | [8 empty] | DS A,1,1 SP A,1,1 SoS ABC,1,1 | DS A,1,2 | DS A,1,3 SoS ABC,1,2 | DS A,1,4 |  |  | DS A,1,5 SoS ABC,1,3 | DS A,1,6 | DS A,1,7 SoS ABC,1,4 | DS A,1,8 | DS A,1,9 SoS ABC,1,5 |  |  | DS A,1,10 SR A,1,1 Retro A,1,1 | System Demo ABC, 1, 1 | DS A,2,1 SP A,2,1 SoS ABC,2,1 | DS A,2,2 | DS A,2,3 SoS ABC,2,2 | DS A,2,4 |  |  | DS A,2,5 SoS ABC,2,3
Legends
DS: Daily Standup
SP: Iteration Planning
SR: Iteration Review
SoS: Scrum of Scrum
Team, Iteration, #
Exploring & researching next PI
Pre PI Planning Context Setting and Readiness
I & A Workshop
PI Planning
Post PI Planning
PI Planning (Distributed Teams)
Continuing Education & Training
Post PI Planning
PI Planning (Distributed Teams)
PI Planning
Coordination with System and Shared Services teams
Coordination with System and Shared Services teams
In converstaion with mgmt & stakeholders
In converstaion with mgmt & stakeholders
In converstaion with mgmt & stakeholders
In converstaion with mgmt & stakeholders
Coordination with System and Shared Services teams
Coordination with System and Shared Services teams
Eliminate Impediments & Supports PO
Eliminate Impediments & Supports PO
Eliminate Impediments & Supports PO
Eliminate Impediments & Supports PO
Coordination with System and Shared Services teams
Coordination with System and Shared Services teams
In converstaion with mgmt & stakeholders
In converstaion with mgmt & stakeholders
Eliminate Impediments & Supports PO
Eliminate Impediments & Supports PO
In converstaion with mgmt & stakeholders
In converstaion with mgmt & stakeholders
Coordination with System and Shared Services teams
Coordination with System and Shared Services teams
Eliminate Impediments & Supports PO
Eliminate Impediments & Supports PO
Coordination with System and Shared Services teams
Coordination with System and Shared Services teams
In converstaion with mgmt & stakeholders
In converstaion with mgmt & stakeholders
Eliminate Impediments & Supports PO
Eliminate Impediments & Supports PO
In converstaion with mgmt & stakeholders
Coordination with System and Shared Services teams
Eliminate Impediments & Supports PO
Coordination with System and Shared Services teams
In converstaion with mgmt & stakeholders
Eliminate Impediments & Supports PO
Coordination with System and Shared Services teams
In converstaion with mgmt & stakeholders
Eliminate Impediments & Supports PO
In converstaion with mgmt & stakeholders
Coordination with System and Shared Services teams
Eliminate Impediments & Supports PO

## PO
2018-02-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on | Tue | Wed
[6 empty] | 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Team A PO | [11 empty] | DS A,1,1 SP A,1,1 PO Sync ABC,1,1 | DS A,1,2 | DS A,1,3 PO Sync ABC,1,2 | DS A,1,4 |  |  | DS A,1,5 PO Sync ABC,1,3 | DS A,1 6 | DS A,1,7 PO Sync ABC,1,4 | DS A,1,8 | DS A,1,9 PO Sync ABC,1,5 |  |  | DS A,1,10 SR A,1,1 Retro A,1,1 | System Demo ABC, 1, 1 | DS A,2,1 SP A,2,1 PO Sync ABC,2,1 | DS A,2,2 | DS A,2,3 PO Sync ABC,2,2 | DS A,2,4 |  |  | DS A,2,5 PO Sync ABC,2,3 | DS A,2,6 | DS A,2,7 PO Sync ABC,2,4
2018-03-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on | Tue | Wed | Thru | Fri | Sat
[6 empty] | 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Team A PO | [5 empty] | DS A,2,8 | DS A,2,9 PO Sync ABC,2,5 |  |  | DS A,2,10 SR A,2,1 Retro A,1,1 | System Demo ABC, 2, 1 | DS A,3,1 SP A,3,1 PO Sync ABC,3,1 | DS A,3,2 | DS A, 3, 3 PO Sync ABC,3,2 | DS A,3,4 |  |  | DS A,3,5 PO Sync ABC,3,3 | DS A,3,6 | DS A,3,7 PO Sync ABC,3,4 | DS A,3,8 | DS A,3,9 PO Sync ABC,3,5 |  |  | DS A,3,10 SR A,3,1 Retro A,3,1 | System Demo ABC, 3, 1 | DS A,4,1 SP A,4,1 PO Sync ABC,4,1 | DS A,4,2 | DS A,2,3 PO Sync ABC,4,2 | DS A,4,4 |  |  | DS A, 4, 5 PO Sync ABC,4,3 | DS A,4,6 | DS A, 4, 7 | DS A,4,8 PO Sync ABC,4,4 | DS A,4,9
2018-04-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on
| 1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  | 24 | 25 | 26 | 27 | 28 | 29 | 30
Team A PO |  | DS A, 4, 10 | System Demo ABC, 4, 1 | [8 empty] | DS A,1,1 SP A,1,1 PO Sync ABC,1,1 | DS A,1,2 | DS A,1,3 PO Sync ABC,1,2 | DS A,1,4 |  |  | DS A,1,5 PO Sync ABC,1,3 | DS A,1,6 | DS A,1,7 PO Sync ABC,1,4 | DS A,1,8 | DS A,1,9 PO Sync ABC,1,5 |  |  | DS A,1,10 SR A,1,1 Retro A,1,1 | System Demo ABC, 1, 1 | DS A,2,1 SP A,2,1 PO Sync ABC,2,1 | DS A,2,2 | DS A,2,3 PO Sync ABC,2,2 | DS A,2,4 |  |  | DS A,2,5 PO Sync ABC,2,3
Legends
DS: Daily Standup
SP: Iteration Planning
SR: Iteration Review
Team, Iteration, #
Exploring & researching next PI
Pre PI Planning Context Setting and Readiness
I & A Workshop
PI Planning
Post PI Planning
PI Planning (Distributed Teams)
Continuing Education & Training
Post PI Planning
PI Planning (Distributed Teams)
PI Planning
Accepting Stories
Accepting Stories
Just-in-time story elaboration
Just-in-time story elaboration
Just-in-time story elaboration
Just-in-time story elaboration
Accepting Stories
Accepting Stories
Backlog Refinement and Converstaion with PM & Stakeholders
Backlog Refinement and Converstaion with PM & Stakeholders
Backlog Refinement and Converstaion with PM & Stakeholders
Backlog Refinement and Converstaion with PM & Stakeholders
Accepting Stories
Accepting Stories
Just-in-time story elaboration
Just-in-time story elaboration
Backlog Refinement and Converstaion with PM & Stakeholders
Backlog Refinement and Converstaion with PM & Stakeholders
Just-in-time story elaboration
Just-in-time story elaboration
Accepting Stories
Accepting Stories
Accepting Stories
Accepting Stories
Just-in-time story elaboration
Just-in-time story elaboration
Accepting Stories
Just-in-time story elaboration
Prog. Level System Demo
Backlog Refinement and Converstaion with PM & Stakeholders
Backlog Refinement and Converstaion with PM & Stakeholders
Backlog Refinement and Converstaion with PM & Stakeholders
Backlog Refinement and Converstaion with PM & Stakeholders
Backlog Refinement and Converstaion with PM & Stakeholders

## PM
2018-02-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on | Tue | Wed
[6 empty] | 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Team A PO | [11 empty] | 6: PO Sync ABC,1,1; 8: PO Sync ABC,1,2; 12: PO Sync ABC,1,3; 14: PO Sync ABC,1,4; 16: PO Sync ABC,1,5 | System Demo ABC, 1, 1 | PO Sync ABC,2,1 |  | PO Sync ABC,2,2 |  |  |  | PO Sync ABC,2,3 |  | PO Sync ABC,2,4
2018-03-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on | Tue | Wed | Thru | Fri | Sat
[6 empty] | 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Team A PO | [6 empty] | PO Sync ABC,2,5 |  |  |  | System Demo ABC, 2, 1 | 6: PO Sync ABC,3,1; 8: PO Sync ABC,3,2; 12: PO Sync ABC,3,3; 14: PO Sync ABC,3,4; 16: PO Sync ABC,3,5 | System Demo ABC, 3, 1 | PO Sync ABC,4,1 |  | PO Sync ABC,4,2 |  |  |  | PO Sync ABC,4,3 |  |  | PO Sync ABC,4,4
2018-04-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on
| 1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  | 24 | 25 | 26 | 27 | 28 | 29 | 30
Team A PO |  | DS A, 4, 10 | System Demo ABC, 4, 1 | [8 empty] | 10: PO Sync ABC,1,1; 12: PO Sync ABC,1,2; 16: PO Sync ABC,1,3; 18: PO Sync ABC,1,4; 20: PO Sync ABC,1,5 | System Demo ABC, 1, 1 | PO Sync ABC,2,1 |  | PO Sync ABC,2,2 |  |  |  | PO Sync ABC,2,3
Legends
Team, Iteration, #
Exploring & researching next PI
Pre PI Planning Context Setting and Readiness
I & A Workshop
PI Planning
Post PI Planning
PI Planning (Distributed Teams)
Continuing Education & Training
Post PI Planning
PI Planning (Distributed Teams)
PI Planning
Accepting Features
Accepting Features
Customrers, users, and stakeholder interaction
Customrers, users, and stakeholder interaction
Customrers, users, and stakeholder interaction
Customrers, users, and stakeholder interaction
Accepting Features
Accepting Features
Backlog Refinement (Feature level)
Backlog Refinement (Feature level)
Backlog Refinement (Feature level)
Backlog Refinement (Feature level)
Accepting Features
Accepting Features
Customrers, users, and stakeholder interaction
Customrers, users, and stakeholder interaction
Backlog Refinement (Feature level)
Backlog Refinement (Feature level)
Customrers, users, and stakeholder interaction
Customrers, users, and stakeholder interaction
Accepting Features
Accepting Features
Accepting Features
Accepting Features
Customrers, users, and stakeholder interaction
Customrers, users, and stakeholder interaction
Accepting Features
Customrers, users, and stakeholder interaction
Prog. Level System Demo
Backlog Refinement (Feature level)
Backlog Refinement (Feature level)
Backlog Refinement (Feature level)
Backlog Refinement (Feature level)
Backlog Refinement (Feature level)

## RTE
2018-02-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on | Tue | Wed
[6 empty] | 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Team A PO | [11 empty] | 6: SoS ABC,1,1; 7: ART Sync ABC…, 1, 1; 8: SoS ABC,1,2; 12: SoS ABC,1,3; 14: SoS ABC,1,4 ART Sync ABC…, 1, 2; 16: SoS ABC,1,5 | System Demo ABC, 1, 1 | SoS ABC,2,1 | ART Sync ABC…,2, 1 | SoS ABC,2,2 |  |  |  | SoS ABC,2,3 |  | SoS ABC,2,4 ART Sync ABC…, 2, 2
2018-03-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on | Tue | Wed | Thru | Fri | Sat
[6 empty] | 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Team A PO | [6 empty] | SoS ABC,2,5 |  |  |  | System Demo ABC, 2, 1 | 6: SoS ABC,3,1; 7: ART Sync ABC…, 3, 1; 8: SoS ABC,3,2; 12: SoS ABC,3,3; 14: SoS ABC,3,4 ART Sync ABC…, 3, 2; 16: SoS ABC,3,5 | System Demo ABC, 3, 1 | SoS ABC,4,1 | ART Sync ABC…, 4, 1 | SoS ABC,4,2 |  |  |  | SoS ABC,4,3 |  | SoS ABC,4,4 ART Sync ABC…, 4, 2 |  | SoS ABC,4,5
2018-04-01 | Sun | Mon |  | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | Mon | Tue | Wed | Thru | Fri | Sat | Sun | M on |  | Tue | Wed | Thru | Fri | Sat | Sun | M on
| 1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  | 24 | 25 | 26 | 27 | 28 | 29 | 30
Team A PO |  | DS A, 4, 10 | System Demo ABC, 4, 1 | [8 empty] | 10: SoS ABC,1,1; 11: ART Sync ABC…, 1, 1; 12: SoS ABC,1,2; 16: SoS ABC,1,3; 18: SoS ABC,1,4 ART Sync ABC…, 1, 2; 20: SoS ABC,1,5 | System Demo ABC, 1, 1 | SoS ABC,2,1 | ART Sync ABC…,2, 1 | SoS ABC,2,2 |  |  |  | SoS ABC,2,3
Legends
SoS: Scrum of Scrum
Team, Iteration, #
Exploring & researching next PI
Pre PI Planning Context Setting and Readiness
I & A Workshop
PI Planning
Post PI Planning
PI Planning (Distributed Teams)
Continuing Education & Training
Post PI Planning
PI Planning (Distributed Teams)
PI Planning
Coordination and collaboration with Management
Coordination and collaboration with Management
Coordination and collaboration with Management
Coordination and collaboration with Management
Coordination among different ARTs of the same program
Coordination among different ARTs of the same program
Coordination among different ARTs of the same program
Coordination among different ARTs of the same program
Coordination and collaboration with Management
Coordination and collaboration with Management
Coordination among different ARTs of the same program
Coordination among different ARTs of the same program
Coordination and collaboration with Management
Coordination and collaboration with Management
Coordination and collaboration with Management
Coordination and collaboration with Management
Coordination and collaboration with Management
Prog. Level System Demo
Coordination among different ARTs of the same program
Coordination among different ARTs of the same program
Coordination among different ARTs of the same program
Coordination among different ARTs of the same program
Coordination among different ARTs of the same program